## Sheet1
Charter: Project LaCEM (Version: V_1.0 – 2021.07.01)
(1) Project Title: |  | Project Laboratory Communication Enhancement and Management (Project LaCEM)
(2) Project Description: |  | To develop a template infrastructure, documents, and the necessary project management training videos that shall aid the DSA690 professional labs and internships.
(3) Project Manager(s): |  |  |  | (4) Date Approved by PM(s): |  | (5) Signature(s) of PM(s):
Heather Campbell (HC)
(6) Project Owner(s): |  |  |  | (7) Date Approved by PO(s): |  | (8) Signature of PO(s):
A. H. Fernando (AF)
(9) Project Sponsor(s): |  |  |  | (10) Date Approved by Sponsor(s): |  | (11) Signature of Sponsor(s):
Joaquin Carbonara (JC)
(12) Business Case: |  | Introduction: DSA MS and PSMs in general are aligned with the non-academic community (industry, government, etc.). One tool to accomplish that goal is a "capstone" course that includes experiential learning (internship, projects, networking, etc.). In DSA MS the course DSA 690 plays that role. Because of wanting to be aligned with the economic, social and political communities, DSA 690 needs to continuously be updated. Problem: Lack of communication, time management, and an operational framework in the DSA690 Professional Labs and Internships. Negative Outcomes: ● Scope Creep: Sponsor has the freedom to keep asking for more ● Confusion: No one including the instructor is completely aware what the actual project is or what every team member is supposed to be doing. At times, one would question what their own tasks are. ● Schedule Overrun: There is no set schedule and therefore, there is lack of accountability resulting is uncompleted delivery items on-time. ● Under Delivery: When a student is close to graduating, instructors make adjustments so they could in fact graduate on-time. This is a classic case of trying to fit the scope into a schedule.
(13) Expected Goals:
Goal # | Goal |  |  | Description
G_01 | Project Communication |  |  | To improve communication within all future projects under DSA690 by the use of SOPs.
G_02 | Project Goal Setting |  |  | To help setup SMART goals for all projects.
G_03 | Project Time Management |  |  | To automate as many project activities as possible to minimize unexpected circumstantial delays.
G_04 | Project Strategy |  |  | To adopt the mentality “under promise and over deliver” on all aspects of all future projects.
G_05 | Project Organization |  |  | To standardize a template project infrastructure for all projects.
G_06 | Student Career Development |  |  | To provide students a high quality project experience through the use of project management.
(14) Project Deliverables:
Element # | Deliverable |  |  | Description
01.00.00 | Infrastructure |  |  | <CELL IS LEFT BLACK ON PURPOSE>
01.01.00 |  |  |  | Decide on a platform to be used for the general project infrastructure
01.02.00 |  |  |  | Create a template folder structure to be used
01.03.00 |  |  |  | Upload the necessary document templates and resources
02.00.00 | Document and Chat Templates |  |  | <CELL IS LEFT BLACK ON PURPOSE>
02.01.00 |  |  |  | Business Case Document Template
02.02.00 |  |  |  | Project Initiation Document Template
02.03.00 |  |  |  | Work Breakdown Structure (WBS) Document Template
02.04.00 |  |  |  | Project Charter Document Template
02.05.00 |  |  |  | Sprint Burndown Chat Template
02.06.00 |  |  |  | RACI Matrix Template
03.00.00 | Welcome video |  |  | <CELL IS LEFT BLACK ON PURPOSE>
04.00.00 | Training Videos |  |  | <CELL IS LEFT BLACK ON PURPOSE>
04.01.00 | Overview Videos |  |  | <CELL IS LEFT BLACK ON PURPOSE>
04.01.01 |  |  |  | What is a Project?
04.01.02 |  |  |  | What is Project Management?
04.02.00 | Project Execution Frameworks |  |  | <CELL IS LEFT BLACK ON PURPOSE>
04.02.01 |  |  |  | What is Agile and how to use it?
04.02.02 |  |  |  | What is SCRUM and how to use it?
04.02.03 |  |  |  | What is KANBAN and how to use it?
04.02.04 |  |  |  | What is SCRUMBAN and how to use it?
04.03.00 | Managing a Project from A-Z |  |  | <CELL IS LEFT BLACK ON PURPOSE>
04.03.01 |  |  |  | What is a Feasibility Study and why is it important?
04.03.02 |  |  |  | What are Project Risk Items and how to manage them?
04.03.03 |  |  |  | What are Project Constraints and how to manage them?
04.03.04 |  |  |  | What is a Business Case Document and how to use it?
04.03.05 |  |  |  | What is a Project Initiation Document and how to use it?
04.03.06 |  |  |  | What is a Work Breakdown Structure and how to use it?
04.03.07 |  |  |  | What are Key Performance Indicators (KPIs)?
04.03.08 |  |  |  | What are Key Decision Points (KDPs)?
04.03.09 |  |  |  | What are Key Responsibility Areas (KRAs)?
04.03.10 |  |  |  | What is a Project Charter and how to use it?
04.03.11 |  |  |  | What is a Sprint Burndown Chat and how to use it?
04.03.12 |  |  |  | What is a RACI Matrix and how to use it?
04.04.00 | Common Project Roles |  |  | <CELL IS LEFT BLACK ON PURPOSE>
04.04.01 |  |  |  | What is the role of a Project Sponsor and what are his/her/their responsibilities?
04.04.02 |  |  |  | What is the role of a Project Owner and what are his/her/their responsibilities?
04.04.03 |  |  |  | What is the role of a Project Manager and what are his/her/their responsibilities?
04.04.04 |  |  |  | What is the role of a Team Member and what are his/her/their responsibilities?
05.00.00 | Keyword Dictionary |  |  | A list on commonly used project management language.
(15) Key Performance Indicators (KPIs):
KPI # | Key Performance Indicator (KPI)
KPI_01 | All team members must attend at least 80% of project meetings
KPI_02 | Three 15-20min stand-up meetings must be held every week with a quorum of 75% for each meeting.
KPI_03 | Average weekly email reply time must be less than 6 hours for the entire team
KPI_04 | Average blocker turn-over must be a maximum of 2 meeting periods per sprint
KPI_05 | Average weekly WBS deliverable delays must be less than 2 hours for the entire team
(16) Risks and Constraints:
Risks: |  | Risk # | Description
|  | R_01 | Lack of familiarity with project management principles
|  | R_02 | Lack of familiarity with project management documents and charts
|  | R_03 | Lack of experience managing stakeholders
|  | R_04 | Lack of familiarity with project feasibility assessment methods
|  | R_05 | Training of students to use PM tools in projects when they have a deadlines to meet with other classes
Constraints: |  | Constraint # | Description
|  | C_01 | Limited time availability to educate the Project LaCEM team on project management principles
|  | C_02 | Limited funding to facilitate formal project management training online
|  | C_03 | Project buy-in resistance by the high influence stakeholders on the use of project management tools for DSA690
|  | C_04 | Have not found a Key Point Person (KPP) to serve as the Project Owner (PO) for DSA690
|  | C_05 | Have not finalized on a project deployment infrastructure
(17) Project Milestones:
WBS # | From | To | Project Phase | Description
WBS_01 | 2021.06.15 | 2021.07.01 | PHASE_01 | Feasibility Study
WBS_02 | 2021.07.01 | 2021.07.05 | PHASE_02 | Project Initiation
WBS_03 | 2021.07.05 | 2021.07.06 | PHASE_03 | Project Infrastructure Setup
WBS_04 | 2021.07.07 | 2021.07.28 | PHASE_04 | Execution
WBS_05 | 2021.07.28 | 2021.07.30 | PHASE_05 | Closeout
(18) Key Decision Points (KDPs):
Date |  | KDP |  | Description
2021.07.07 |  | KDP_01 |  | Hand-off SP1
|  | KDP_02 |  | Update SP1
|  | KDP_03 |  | Close-out SP1 and Hand-off SP2
|  | KDP_04 |  | Update SP2
|  | KDP_05 |  | Close-out SP2 and Hand-off SP3
|  | KDP_06 |  | Update SP3
|  | KDP_07 |  | Close-out SP3 and Hand-off SP4
|  | KDP_08 |  | Update SP4
2021.07.28 |  | KDP_09 |  | Close-out SP4
2021.07.30 |  | KDP_10 |  | Project Close-out
(19) Team Members:
Member # | Name |  |  | Role | Key Responsibility Areas (KRAs)
M_00 | ALL |  |  | ALL | Dedicate a minimum of 4 working hours per week for the project activities
All project members must be alert - check emails at least a minimum of 4 times every 24 hours to make sure the smooth execution of the project through a heightened sense of communication.
Follow the project standard operations procedures (SOPs) as put in place by the team for maximum resolution in communication and timely project delivery.
Dedicate a suitable amount of time on continuous improvement and professional development by actively learning about project management tools, protocols, and standard operations procedures while applying them to this project (Maintain a training log)
Object as soon as possible, whenever necessary, on an action item that is assigned is outside of the members skill set to ensure the action item in question is assigned to someone else who is capable of the task.
M_01 | Joaquin Carbonara (JC) |  |  | Active Member / Sponsor | Serve as the Project Sponsor
Consult with PM_SME&Coach and write the business case
Seek advice from PM_SME&Coach out side of the scheduled weekly 4 hours for professional development to discuss issues of the project that need solving or confusion in regards to the SOPs.
Carry out project tasks assigned by the PM as per the WBS.
Contact PO if and when there are question regarding the project
M_02 | A. H. Fernando (AF) |  |  | Active Member / PO / PM_SME&Coach | Serve as the Project Owner / PM_SME&Coach
Serve as a PM coach to the sponsor, manager, and rest of the project team as necessary regarding PM methodologies.
Carry out project tasks assigned by the PM as per the WBS.
Contact Sponsor if and when there are question regarding the business case and PM regarding the project.
M_03 | Heather Campbell (HC) |  |  | Active Member / PM | Serve as the Project Manager (PM)
Assess member availability and setup all project meetings
Maintain the project burn-down chart
Maintain the Work Breakdown Structure (WBS)
Seek advice from PM_SME&Coach out side of the scheduled weekly 4 hours for professional development to discuss issues of the project that need solving or confusion in regards to the SOPs.
Carry out project tasks assigned by the PO.
Contact PO if and when there are question regarding the business case / project initiation and active team members regarding the project.
M_04 | Tiffany Fuzak (TF) |  |  | Active Member / Consultant | Serve as a Project Consultant (Student Experience)
Seek advice from PM_SME&Coach out side of the scheduled weekly 4 hours for professional development to discuss issues of the project that need solving or confusion in regards to the SOPs.
Carry out project tasks assigned by the PM as per the WBS.
Contact PO if and when there are any questions, concerns, and/or recommendations.
(20) Attachments to the Charter: RACI Matrix, Standard Operations Procedures (SOPs), Work Breakdown Structure (WBS), Technical Review Milestone Document (Goes along with the KDPs), etc.
By: A. H. Fernando