## Basic Project RACI
Roles
Critical Activity | JC (Project Sponsor) | AF (Project Owner) | HC (Project Manager) | JC, AF, HC, TF (Team Members) | AF, TF (Consultant) | Melissa and Wende (External Stakeholder) | Murray, Bill, Karen (External Stakeholder)
Develop Business Case | R | A | C | C | C | I | I
Project Feasibility | C | R/A | C | C | C | I | I
Project Intiation Document | I | A | R | C | C | I | I
WBS | I | I | R/A | C | C | I | I
Project Charter | I | A | R | C | C | I | I
RACI matrix | I | I | R/A | C | C | I | I
Sprint Burndown Chart | I | I | R/A | I | I | I | I
Schedule and conduct Project LaCEM meetings | I | I | R/A | C | C | I | I
Provide progress on performance metrics (KPIs) | I | I | R/A | R | R | I | I
Build deliverables (powerpoints) | I | I | A | R | R | I | I
Test deliverables | I | I | R/A | R | R | I | I
Approve deliverables | C | A | R | I | I | I | I

## RACI Definitions
KEY | R = Responsible | Responsible for performing the task (ie. the actual person doing the work to complete the task).
| A = Accountable | Ultimately accountable for the task being done in a satisfactory manner. The accountable person must sign-off the work that the Responsible person produces.
| C = Consulted | Team members whose input is used to complete the task, usually an SME or team of SMEs involved. Communication with these stakeholders will be 2-way in nature.
| I = Informed | Team members who are informed as to the status of the task. These are typically stakeholders with the highest authority or stakeholders who are external. Communication with these stakeholders will be 1-way in nature.