## <Project Designation> - WBS
Work Breakdown Structure (WBS) Document
<Project Designation>
<Organization and/or Group Name>
| Project Manager: | JohnJane Doe
| Today's Date: | 2021-07-01
| Start Date: | 2021-07-07 |  | 2021-07-07 | [5 empty] | 0 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03
WBS # | User Stories / Action Items / Tasks | Task Lead Initials | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2021-07-05: 2021-07-05; 2021-07-12: 2021-07-12; 2021-07-19: 2021-07-19; 2021-07-26: 2021-07-26; 2021-08-02: 2021-08-02; 2021-08-09: 2021-08-09; 2021-08-16: 2021-08-16; 2021-08-23: 2021-08-23; 2021-08-30: 2021-08-30; 2021-09-06: 2021-09-06; 2021-09-13: 2021-09-13; 2021-09-20: 2021-09-20; 2021-09-27: 2021-09-27; 2021-10-04: 2021-10-04; 2021-10-11: 2021-10-11; 2021-10-18: 2021-10-18; 2021-10-25: 2021-10-25; 2021-11-01: 2021-11-01; 2021-11-08: 2021-11-08; 2021-11-15: 2021-11-15; 2021-11-22: 2021-11-22; 2021-11-29: 2021-11-29; 2021-12-06: 2021-12-06; 2021-12-13: 2021-12-13; 2021-12-20: 2021-12-20; 2021-12-27: 2021-12-27; 2022-01-03: 2022-01-03; 2022-01-10: 2022-01-10; 2022-01-17: 2022-01-17; 2022-01-24: 2022-01-24; 2022-01-31: 2022-01-31; 2022-02-07: 2022-02-07; 2022-02-14: 2022-02-14; 2022-02-21: 2022-02-21; 2022-02-28: 2022-02-28; 2022-03-07: 2022-03-07; 2022-03-14: 2022-03-14; 2022-03-21: 2022-03-21; 2022-03-28: 2022-03-28; 2022-04-04: 2022-04-04; 2022-04-11: 2022-04-11; 2022-04-18: 2022-04-18; 2022-04-25: 2022-04-25; 2022-05-02: 2022-05-02; 2022-05-09: 2022-05-09; 2022-05-16: 2022-05-16; 2022-05-23: 2022-05-23; 2022-05-30: 2022-05-30
1 | (L1) Action Item 01 |  | 2021-07-07 | 2021-09-30 | 86 | 38.15% | 62 | 32 | 54 | bar: 0
1.1 | (L2) Action Item 01 |  | 2021-07-07 | 2021-08-17 | 42 | 37% | 30 | 15 | 27
1.1.1 | (L3) Action Item 01 |  | 2021-07-07 | 2021-07-18 | 12 | 33% | 8 | 3 | 9
1.1.2 | (L3) Action Item 02 |  | 2021-07-19 | 2021-08-05 | 18 | 25% | 14 | 4 | 14
1.1.3 | (L3) Action Item 03 |  | 2021-08-06 | 2021-08-17 | 12 | 53% | 8 | 6 | 6
1.2 | (L2) Action Item 02 |  | 2021-07-24 | 2021-08-13 | 21 | 25% | 15 | 5 | 16
1.2.1 | (L3) Action Item 01 |  | 2021-07-24 | 2021-08-13 | 21 | 33% | 15 | 6 | 15
1.2.2 | (L3) Action Item 02 |  | 2021-07-24 | 2021-08-13 | 21 | 17% | 15 | 3 | 18
1.3 | (L2) Action Item 03 |  | 2021-08-14 | 2021-09-20 | 38 | 46% | 26 | 17 | 21
1.3.1 | (L3) Action Item 01 |  | 2021-08-14 | 2021-09-20 | 38 | 46% | 26 | 17 | 21
1.3.2 | (L3) Action Item 02 |  | 2021-08-14 | 2021-09-20 | 38 | 46% | 26 | 17 | 21
1.3.3 | (L3) Action Item 03 |  | 2021-08-14 | 2021-09-20 | 38 | 46% | 26 | 17 | 21
1.3.4 | (L3) Action Item 04 |  | 2021-08-14 | 2021-09-20 | 38 | 46% | 26 | 17 | 21
1.4 | (L2) Action Item 04 |  | 2021-09-13 | 2021-09-30 | 18 | 43% | 14 | 7 | 11
2 | (L1) Action Item 02 |  | 2021-09-30 | 2022-01-11 | 104 | 44.98% | 74 | 46 | 58 | bar: 0
2.1 | (L2) Action Item 01 |  | 2021-09-30 | 2021-11-21 | 53 | 44% | 37 | 23 | 30
2.1.1 | (L3) Action Item 01 |  | 2021-09-30 | 2021-10-19 | 20 | 68% | 14 | 13 | 7
2.1.2 | (L3) Action Item 02 |  | 2021-10-20 | 2021-11-02 | 14 | 49% | 10 | 6 | 8
2.1.3 | (L3) Action Item 03 |  | 2021-11-03 | 2021-11-21 | 19 | 15% | 13 | 2 | 17
2.2 | (L2) Action Item 02 |  | 2021-11-18 | 2021-12-24 | 37 | 45.8% | 27 | 16 | 21
2.2.1 | (L3) Action Item 01 |  | 2021-11-18 | 2021-12-24 | 37 | 92% | 27 | 34 | 3
2.2.2 | (L3) Action Item 02 |  | 2021-11-18 | 2021-12-24 | 37 | 16% | 27 | 5 | 32
2.2.3 | (L3) Action Item 03 |  | 2021-11-18 | 2021-12-24 | 37 | 18% | 27 | 6 | 31
2.2.4 | (L3) Action Item 04 |  | 2021-11-18 | 2021-12-24 | 37 | 40% | 27 | 14 | 23
2.2.5 | (L3) Action Item 05 |  | 2021-11-18 | 2021-12-24 | 37 | 63% | 27 | 23 | 14
2.3 | (L2) Action Item 03 |  | 2021-12-25 | 2022-01-11 | 18 | 44% | 12 | 7 | 11
3 | (L1) Action Item 03 |  | 2022-01-09 | 2022-06-01 | 144 | 41.36% | 103 | 59 | 85 | bar: 0
3.1 | (L2) Action Item 01 |  | 2022-01-09 | 2022-02-20 | 43 | 17.5% | 30 | 7 | 36
| (L3) Action Item 01 |  | 2022-01-09 | 2022-02-20 | 43 | 21% | 30 | 9 | 34
| (L3) Action Item 02 |  | 2022-01-09 | 2022-02-20 | 43 | 14% | 30 | 6 | 37
3.2 | (L2) Action Item 02 |  | 2022-02-21 | 2022-03-12 | 20 | 52.67% | 15 | 10 | 10
| (L3) Action Item 01 |  | 2022-02-21 | 2022-03-12 | 20 | 32% | 15 | 6 | 14
| (L3) Action Item 02 |  | 2022-02-21 | 2022-03-12 | 20 | 52% | 15 | 10 | 10
| (L3) Action Item 03 |  | 2022-02-21 | 2022-03-12 | 20 | 74% | 15 | 14 | 6
3.3 | (L2) Action Item 03 |  | 2022-03-13 | 2022-04-23 | 42 | 46% | 30 | 19 | 23
3.3.1 | (L3) Action Item 01 |  | 2022-03-13 | 2022-04-23 | 42 | 47% | 30 | 19 | 23
3.3.2 | (L3) Action Item 02 |  | 2022-03-13 | 2022-04-23 | 42 | 45% | 30 | 18 | 24
3.4 | (L2) Action Item 04 |  | 2022-04-24 | 2022-06-01 | 39 | 45.5% | 28 | 17 | 22
3.4.1 | (L3) Action Item 01 |  | 2022-04-24 | 2022-05-16 | 23 | 64% | 16 | 14 | 9
3.4.2 | (L3) Action Item 02 |  | 2022-05-17 | 2022-06-01 | 16 | 27% | 12 | 4 | 12
Please follow the following guidelines when filling out this WBS document:
- Modify all shades of GREEN cells and the WBS, Tasks, and Task Lead columns. The rest of the columns are formulas.
- The number of weeks shown in the gantt chart is limited by the maximum number of columns available in Excel.
- The Start Date that you choose determines the first week in the gantt chart, starting on a Monday.
- Use the slider to adjust the range of dates shown in the gantt chart.
- Only 48 weeks can be shown/printed at one time, because each week uses up 5 columns.
Q: The Working Days column shows "###". How do I fix that?
You need to install the Analysis ToolPak add-in that comes with Excel. Go to Tools > Add-ins, and select Analysis ToolPak.
Q: How do I make Task 2 start the day after the end of Task 1?
Use the following formula for the start date of Task 2:
=EndDate+1
where EndDate is the reference to the cell containing the end date of task 1
Q: How do I add/insert tasks and subtasks?
Copy the entire ROW (or a group of rows) for the type of task(s) you want to add and then right-click on the row where you want to insert the new tasks, then select Insert Copied Cells.
Important Note: When inserting a new subtask after the last subtask or before the first subtask, you will need to update the formulas for calculating the Level 1 %Complete and Duration (see below) to include the new subtask, because the ranges won't automatically expand to include the additional row.
Q: How do I calculate the %Complete for a Level 1 task based upon the %Complete of all of the associated subtasks?
Example: If Task 1 is on row 11 and the subtasks are on rows 12-15, use the following formula:
=SUM(F12:F15)/COUNT(F12:F15)
Q: How do I calculate the Duration for a Level 1 task based upon the largest end date of a sub task?
Example: If the Level 1 task is on row 11 and the sub tasks are on rows 12-15, use the following formula
=MAX(D12:D15)-C11
Q: How can I include holidays in the calculation of the Working Days?
You can add a list of holidays to exclude in the NETWORKDAYS function. See Excel's help (F1) for more information.
Q: How do I change the print settings?
Select the entire range of cells that you want to print and then go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling and Page Orientation as desired.
Note on A11: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on D11: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on E11: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on F11: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. For the main tasks, you can calculate the duration by finding the maximum End date of the sub tasks and subtracting the earliest start date. For example: F13=MAX(E14:E17)-D13
Note on G11: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%). For the main tasks, you can use a weighted average of the sub tasks by adding the formula: G13=SUMPRODUCT(F14:F17,G14:G17)/SUM(F14:F17) Note: If you insert rows, make sure that the calculation is updated correctly.
Note on H11: Working Days Counts only Mon-Fri, using the NETWORKDAYS() formula. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached. Note: If the start date is later changed, the number of working days may also change.
Note on I11: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on J11: Calendar Days Remaining This column is calculated by subtracted the Days Complete from the Duration.