## Basic Project RACI
Roles
| Critical Activity | Project Sponsor | External Stakeholder (Consultant) | External Stakeholder (Consultant) | External Stakeholder (Consultant) | Project Owner | Team Lead | Team Members | Project Manager
Vision | Develop strategy & communicate vision | R | A | C | I | I | I | I | I
| Oversee Financial System Governance body | R | A | C | C | I | I | I | I
| Define & monitor performance metrics (KPIs) | C | A | R | C | C | C | C | I
Administration | Schedule and conduct BSC_DSA group meetings | C | C | R+A | C | C | C | C | C
| Establish priorities for ongoing support, maintenance, critical issues and enhancement of the application | C | I | I | A | R | C | C | C
| Manage scope, resources and issues related to system operations and enhancements | C | I | I | A | R | C | C | C
| Cross-functional coordination of ongoing operational concerns, patches, fixes, upgrades, and enhancements | I | I | I | I | A | R | R | I
| Provide progress on performance metrics (KPIs) | A | I | R | I | I | C | C | C
| Provide status and progress of ongoing DSA Project initiatives | A | I | R | C | C | C | C | C
Enhancement Process | Identify opportunities for process and system improvements, evaluate options, propose enhancements | C | I | I | C | A | R | C | C
| Consolidate list of proposed enhancements | I | I | C | A | C | C | C | R
| Define and document business requirements for system enhancements | I | I | I | I | R | C | C | C
| Provide technical estimates and plan for enhancement requests | I | I | I | I | A | C | R | C
| Develop charter for all enhancements for each cycle | I | I | I | A | C | C | C | R
| Review and approve enhancement charter | C | I | I | A | I | I | I | R
| Approve enhancement charter budget | I | A | I | I | I | I | I | R
Please note that this Template is produced through an example for clarity

## RACI Definitions
KEY | R = Responsible | Responsible for performing the task (ie. the actual person doing the work to complete the task).
| A = Accountable | Ultimately accountable for the task being done in a satisfactory manner. The accountable person must sign-off the work that the Responsible person produces.
| C = Consulted | Team members whose input is used to complete the task. Communication with these members will be 2-way in nature.
| I = Informed | Team members who are informed as to the status of the task. Communication with these members will be 1-way in nature.